## Slide 1
Agent_opt
Making a local AI coding agent measurable on a 10 GB graphics card
Project overview for project management. Status: tooling built (M0 to M3), first full baseline measured (M4.1).
14
tasks, each checked automatically
335
automated tests keep the tooling correct
336
baseline runs recorded in two full passes
Notes: Agent_opt is a measurement project: it studies how a locally hosted AI coding agent behaves on a single mid-range graphics card (RTX 3080, 10 GB). The first four milestones built the measuring tools; the first full measurement run (168 runs) is done; the next steps use the tools for experiments. This deck explains why, how, where we are and what we need from you.

## Slide 2: Why measure an AI agent?
An AI coding agent works by asking a language model a long series of questions, with small tool steps in between (read a file, run a test). On a modest graphics card every answer is slow: a typical task takes 1 to 2 minutes, some take 8.
Today the advice for making this faster or better is mostly folklore, and nobody has measured where the time really goes.
Unknown time sinks
We could not say which part of a run is slow, so we could not say what to fix.
Claims without evidence
A setting that looks faster on one run may be noise, or may quietly make answers worse.
Answers that look right
The agent can invent citations or claim tests passed that it never ran.
Notes: The point for a manager: this is a performance and quality question about an AI workload, and until now it has been answered by intuition. The three boxes are the three gaps the project closes: time, evidence, trustworthiness of answers.

## Slide 3: The goal: evidence, not guesses
Find out where an AI agent's time goes on one 10 GB graphics card, and which changes make it faster or better without making it worse.
Measure
Time every model call, every tool step and the graphics card itself, on real tasks.
Experiment
Change one setting at a time and repeat each test 10 times, so luck can be ruled out.
Report
Charts with confidence ranges that anyone can re-check from the recorded runs.
Everything runs locally on one RTX 3080 (10 GB): no cloud models, no extra hardware.
Notes: Keep this to one sentence: we want evidence about where time goes and which fixes work. The local-only constraint is deliberate, it keeps the study reproducible and cheap.

## Slide 4: How the measurement works
Task suite
14 realistic tasks, each with an automatic pass/fail check.
The agent
OpenCode driving a local AI model on the RTX 3080.
Measurement
Every model call is timed; the GPU is sampled 10 times a second.
Verdict
A script, not an opinion, decides if the task was done right.
Statistics
10 repeats per test; results come with confidence ranges.
Every run is recorded. All results can be re-derived later from the recordings alone, with no graphics card and no AI model, so nobody has to trust a screenshot.
Notes: Left to right: a fixed set of tasks goes to the agent, a thin measurement layer records what happens, an automatic check judges the result, and statistics turn many runs into conclusions. The bottom line is the reproducibility promise.

## Slide 5: Why the results can be trusted
Automatic pass/fail
14 tasks are judged by code: compile and run, unit tests, fact checks.
Repeat and shuffle
10 runs per test, in random order, with recorded random seeds.
Measure the measurer
Extra runs without our probe show it does not distort the results.
Clear statistics
Confidence ranges everywhere; nothing is claimed from fewer than 5 runs.
Self-testing tooling
335 automated tests; results are re-derived from recordings on every change.
Failures stay visible
Negative results and past measurement bugs are documented, not hidden.
Notes: This is the quality story for a manager: the numbers will be reproducible and statistically defensible. One example of why it matters: in an early check, two tasks that passed in single runs actually pass only about 40 percent of the time. The full baseline confirmed it: only 4 of 14 tasks passed every time in 10 runs.

## Slide 6: Where we are: tooling built, first data in
Build phase: complete
Measurement phase: first run done
M0 Baseline and setup
M1 Task suite
M2 Run and measure
M3 Statistics and reports
M4
M4 Baseline campaign
M5
M5 Experiments
M6
M6 Citation checker
M7
M7 Write-up
M0 to M3 delivered
14-task suite with automatic checks, a repeatable test runner, GPU and timing measurements, statistics, report generator, and a replay mode that re-derives every result.
M4.1 done, M4.2 next
The whole suite ran 10 times per task, twice (336 runs). Removing a leaked block from the prompt made runs about 42% faster. Next: repeat with a smaller memory window (16k).
Notes: Eight milestones in total. The first four built and verified the measuring equipment; that part is finished and tested. The first full run (M4.1) is complete; the next steps compare settings against it.

## Slide 7: What the baseline shows
Where the time goes, by task type
Chart: 
| Long context | Log triage | Research | Refactor | Bug fix | Repo Q&A | Email / calendar | Reasoning | Code generation | Code review | All tasks
Model reads its instructions (prefill) | 70.9 | 63.6 | 56.7 | 40 | 36.3 | 35.1 | 31.3 | 28 | 16.2 | 11.1 | 33.1
Model writes the answer (decode) | 26.2 | 34.8 | 36.9 | 57.5 | 58.2 | 59 | 55.4 | 59.4 | 76.8 | 85.1 | 60.5
Tools and overhead | 3 | 1.5 | 6.4 | 2.5 | 5.5 | 5.9 | 13.2 | 12.6 | 7 | 3.9 | 6.3
Passed out of 10 runs, per task
Chart: 
| Moving average (bugfix) | Dir stats (code gen) | Confirm send (comms) | Tidal report (long ctx) | Scientific (reasoning) | Rename (refactor) | FizzBuzz (code gen) | Pool exhaustion (logs) | Compression (code gen) | sqrt (code review) | Retry policy (repo Q&A) | Ring buffer (code gen) | Tax rates (reasoning) | Free will (research)
Runs passed (of 10) | 10 | 10 | 10 | 10 | 9 | 9 | 8 | 8 | 6 | 5 | 5 | 3 | 3 | 3
42%
faster per run once a block of personal setup was removed from the prompt. Success is unchanged within noise (71% vs 74%).
60%
of the time is now the model writing answers. Reading its instructions fell from 54% to 33%.
71%
of runs passed overall (99 of 140). Only 4 of 14 tasks passed every time.
Notes: Source: the isolated baseline run, 14 tasks x 10 runs at the 32k setting, 140 measured runs. Left: share of wall-clock time; the model's reading of its instructions (prefill) dominates for long-context and reasoning tasks, writing the answer dominates for code generation. Right: runs passed per task; with 10 runs each, only the extremes are clearly different (the research task needs a larger memory window and passed 1 of 10). The earlier two-run pilot suggested 75 percent prefill; the first full run showed 54 percent, and after the leaked block was removed it is 33 percent, with writing the answer now the largest share (60 percent). The 42 percent speed-up is a median over all tasks, with a confidence range of 37 to 48 percent. About 40 percent of the saved time comes from the shorter prompt and the rest from the model reusing its already-processed prompt between runs; that second part depends on runs following each other. Instrumentation overhead check is still inconclusive.

## Slide 8: What happens next
M4
Baseline runs
first run done; 16k run about 5 hours
Done: whole suite, 10 repeats per task
Next: re-check the earlier 16k vs 32k finding
Time breakdown per task type (done for 32k)
M5
Experiments
7 to 8 days
Memory size of the context window
Shorter agent instructions
Faster answering with a draft model
A second model, task-specific agents
M6
Citation checker
4 to 5 days
Automatic check of every cited study
Measure invented citations before and after
M7
Write-up
3 to 4 days
README with the results first
Slide deck
Summary numbers for reuse
Notes: Roughly three more working weeks of effort, with long unattended GPU runs in M4 and M5. M4 is the immediate next step and is highlighted. The experiments in M5 are the heart of the project: each lever is tested against the baseline with confidence ranges.

## Slide 9: What “done” looks like
14 × 10 × 6
tasks × repeats × configurations
about 840 measured runs, all with confidence ranges
At least 2 changes proven to help, and at least 1 clear negative result with its cause
Invented-citation rate measured on 20 or more research questions, with and without the checker
One chart answering: what share of an agent's time is the GPU generating text?
Measurement overhead shown to be under 5%
Deck, README and summary numbers ready to share
Notes: These are the plan's success criteria in plain language. The rule behind 'proven to help': the confidence range of the improvement must exclude zero and success rate must not drop by more than 5 percentage points.

## Slide 10: Risks and decisions we need
Risks
Machine time
10 repeats took about 4.3 hours for one setup; the full sweep is estimated at 25 hours of GPU time.
Too many easy tasks
Four of 14 tasks pass every time, so they cannot show an improvement; some may need to be made harder.
One graphics card
Results hold for this RTX 3080 only; other hardware is out of scope.
Decisions needed
1
Approve overnight GPU time
About 40 hours of unattended runs spread over several nights.
2
Settle the sweep scope
If time runs short, drop in this order: second model, flash attention, 8k context.
3
Handle the research task
It passed only 1 of 10 runs at the baseline memory window and needs a larger one: keep it as a special case?
Notes: The main ask is machine time: the statistically sound version of the experiments needs long unattended runs. The other two decisions are scoping choices that keep the project inside its planned effort.